## Experiment_Timeline
Task | Deadline | Checklist
Order seeds | End of November 2020 | X
Order Pots | 2020-12-01
Start to germinate seeds | 2020-12-01
have Germinated seeds | 2021-04-01
Obtain Soil | 2021-03-15
Start experiment | 2021-05-01
Order soil | 2021-01-01
Book greenhouse space | 2021-01-11
Book Growth chamber space | 2021-01-11
Start cold stratification for Abies | 2021-01-11
Start cold stratification for Picea | 2021-03-15
Mix field/store bought soil | 2021-03-25

## Experiment_Budget
Equipment | Cost | 5 replicates | 7 replicates | 10 replicates
Pots (https://www.leevalley.com/en-ca/shop/garden/planting/potting/10643-4-inch-plastic-pots?item=BL292) | 41.50 per 100 | 160 pots needed thus $81.50 | 224 pots needed thus $124.50 | 320 pots needed thus $166
Field Soil (Alex Fraser) | Free | Free | Free | Free
Growing soil (BroadwayStore@HuntersGardenCentre.com) | $9.99 per 28 L | 19.98 | 19.98 | 29.97
Seeds (spencer.reitenbach@gov.bc.ca) | Free | Free | Free | Free